## Slide 1
Purpose and Scope
The purpose of this document is to provide a written procedure for New Product Introduction (NPI). The NPI is a structured phase-gate process for transitioning new products from Design into Production Manufacturing. This procedure defines the roles and responsibilities of each phase, the typical activities performed at each phase, and the expected outputs. This procedure is used to monitor the progress, risks, and costs of a design project.
Responsibility
  Owners
    The Engineering Managers, Quality Managers, Materials Manger, and Manufacturing manager are owners are responsible for controlling this document.
  Coordinator
    The Quality Manager is the coordinator of this process. Ensures NPI Milestone meetings are updated regularly.
  The Product Manager oversees this process and assists with establishing priorities.
  The Engineering project manager is responsible for managing the engineering phases of the project and supporting the transition into manufacturing.
  Manufacturing project manager is responsible for managing the transition into manufacturing.
  Engineering, manufacturing, and materials personnel are responsible for following this procedure in developing new products.
Related Documents | 
Document Title | Document Number

## Slide 2: Overview
The Goal
The goal of the NPI process is to successfully transition the product design from concept through engineering to manufacturing. To achieve this goal, the NPI process flows through a series of phases that are linked to product design and development, according to the Design and Development Procedure and project milestones. Each phase has a specific purpose with a list of activities/actions to achieve that purpose. The process is intended to act as a framework for Major Projects. There are 8 phases in the process:
The Phases
Phase 0 – Market Research (Optional for BZN and usually originating through demands from other TDY FLIR sites)
Phase 1 – Concept
Phase 2 – Planning
Phase 3 – Preliminary Design
Phase 4 – Critical Design
Phase 5 – Engineering Launch
Phase 6 – Manufacturing Launch
Phase 7 – Support
During each phase various departments are responsible for respective phase-related activities. The foundation of this process is based on integrated development teams which consist of representatives from core functional areas such as Engineering, Product Management, Manufacturing, Sales, Procurement, Service, Marketing, and Quality.
Exit Criteria (Gates)
NPI Milestone meetings are held to review the status of each phase and serves the purpose of managing risks and determining whether the project is ready to move to the next phase. Tasks associated with each phase are tracked using the NPI Phase Checklist Form. The checklist form is intended to be tailored to suit projects of various size and complexity.
Product manager, Engineering project manager, Manufacturing project manager formally approve transition to the next phase through signatures on the NPI Phase Approval Form or through e-mail approval attached to the form. Signed forms are stored in respective project folders in the following location. Hardcopies in binders, electronic copies in folders.
In some circumstances, it may be desirable for the development team to begin activities in the next phase (up to one phase ahead of the current phase) in advance of approval of the current phase. This is allowed if approved by all the current phase signatories or their designees.

## Slide 3: Phase 0: Market Research
Overall Responsibility
The Business Development group is primarily responsible for the work done during this phase.
Purpose of the Phase
The Market Research phase is used to determine the feasibility of a new technology and to determine whether a market exists or could be created for a potential product. The organization may explore new technologies and markets to obtain enough information to conceptualize a new product. When a new product concept doesn’t rely on new technology or markets, this phase is omitted from the process.
The purpose of this phase is to perform fundamental technical development for a potential product and assess feasibility. Technologies will be evaluated, explored, and developed to the breadboard stage.
Phase 1: Concept
Overall Responsibility
The Product Manager and Engineering Manager are primarily responsible for the work done during this phase.
Purpose of the Phase
The Concept phase is used to take a product idea and expand it in sufficient detail and with sufficient market research for evaluation as a product. This phase is intended to be tailored based on the scope, complexity, and uncertainty regarding the product in question. In general, this phase is used to develop major new products and conduct feasibility studies.
The purpose of this phase is to determine feasibility. The output of this phase is to define the target market, customer requirements and product adequately for generating a Product Requirements Document.

## Slide 4: Phase 2: Planning
Overall Responsibility
Engineering and Product Management are primarily responsible for the work done during this phase. Manufacturing begins to be involved as manufacturing input are required to complete the Project Plan and their participation in key reviews is necessary.
Purpose of the Phase
The purpose of this phase is to identify Engineering Project Manager
who comprehensively plans the project through the NPI process and creates a system design appropriate to the requirements of the Product Requirements document.
Key outputs in this phase are the
Project Plan (Per the Design and Development Procedure)
Product Specifications document
Engineering Functional Requirements document
Phase 3: Preliminary Design
Overall Responsibility
The Engineering group is primarily responsible for the work done during this phase. Manufacturing group involvement ramps up with increased participation in design reviews and development of the Manufacturing Plan. The preferred method is the use of the Manufacturing Plan Checklist.
Purpose of the Phase
The purpose of this phase is to conduct preliminary engineering design activities culminating in a Preliminary Design Review (PDR). Building and testing engineering subassemblies is done in this phase.
Phase 4: Critical Design
Overall Responsibility
The Engineering group is primarily responsible for the work done during this phase. Manufacturing group involvement continues to ramp up with many of the same activities performed during phase 3.
Purpose of the Phase
The purpose of this phase is to conduct detailed engineering design activities, culminating in a Critical Design Review (CDR). Building and testing of EDM (Also known as Beta) hardware is the main method by which the design is validated against the requirements. EDM hardware is defined as proof of concept hardware that cannot be sold to a customer and is not representative of standard manufacturing processes.

## Slide 5: Phase 5: Engineering Launch
Overall Responsibility
In this phase the Engineering group has primarily responsibility with assistance from Manufacturing. This phase begins the transition of the product design from engineering to manufacturing production, with the effort being led by engineering.
Purpose of the Phase
The purpose of this phase is to build a small quantity of product, designated as LRIP (Low Rate Initial Production) units, in a manner consistent with the expected production processes to validate completion of design through DVT and to develop, implement, and refine the production process. LRIP units are built on the production floor primarily by Engineering with manufacturing support.
The objective of building LRIP units is to:
Provide production configured or representative units for operational testing and DVT
Establish and validate the necessary tooling, equipment, documentation, material, and supplier base to support an orderly increase in the production rate, and sufficient to support full rate production upon successful completion of the PRR.
Qualified LRIP units may be delivered to customers after quality assurance steps (ESS through ATP). The customers receiving these units are notified they are receiving LRIP units and their feedback in support of the development process is solicited.
At the completion of this phase, the majority of the engineering documentation is completed and released. Subassemblies and components can be released to alpha rev through the ECO procedure provided all Engineering and manufacturing activities for those parts have been completed (e.g. DVT completed, incoming inspection tests defined, suppliers qualified).
Phase 6: Manufacturing Launch
Overall Responsibility
In this phase the manufacturing group has primarily responsibility with assistance from Engineering. This phase completes the transition of the product design from engineering to manufacturing production, with the effort being led by Manufacturing.
Purpose of the Phase
The purpose of this phase is to build production units and finalize production processes, tooling, fixtures, and resource training. During the Manufacturing Launch phase, the production units are built by Manufacturing with decreasing engineering support.
Objectives of this phase
Release remaining assemblies, subassemblies, and components to production (alpha level)
Build systems to required specifications using manufacturing processes and systems (fixtures, tooling)
Finalize Manufacturing documentation
Engineering performs tests on selected units to validate that the product was manufactured as intended and meets product requirements.
At the completion of this phase, the product is considered to be completely transitioned into production.

## Slide 6: Phase 7: Support
Overall Responsibility
The Manufacturing group is primarily responsible for the work done during this phase. Engineering always plays a critical role in supporting the product throughout product life cycle.
Purpose of the Phase
The purpose of this phase is the continuation of product support, maintenance, margin improvement, quality improvement and to enhance the product through the end of its product life cycle.

## Slide 7: Appendix A: Acronyms
Acronym | Definition
ATP | Acceptance Test Plan
CDR | Critical Design Review
DFM | Design For Manufacturability
DVT | Design Verification Testing
EDM | Engineering Development Material
ENG | Engineering
FAI | First Article Inspection
ICD | Interface Control Drawings and/or Interface Control Documents
LRIP | Low Rate Initial Production, based on DoD 5000, tailored for TDY FLIR’s application
MFE | Manufacturing Engineering
N/A | Not Applicable
NPI | New Product Introduction
OPS | Operations
PDR | Preliminary Design Review
PLM | Product Line Management
PRR | Production Readiness Review
SDD | Software Design Document
SRR | System Requirements Review
SVC | Service
TRR | Test Readiness Review

## Slide 8: Appendix B: Design Reviews defined
Listed below are the definitions for the various reviews held during engineer product development. For small projects these reviews may be combined into one meeting. For large project each review may be broken down into a number of sub-reviews (by feature, engineering discipline, etc). Meeting minutes and attendance sheets may be used as evidence of the meeting occurrence.
Review | Description
Systems Concept Review (SCR) | This review is held with business development, product management and engineering. The purpose is to review the basic product concept and get feedback on market size, features, technical feasibility, and technical effort.
System Requirements Review (SRR) | This review is held with engineering and product marketing. The intent is to confirm that the engineering requirements meet the customer expectations and are achievable with available resources
System Architecture Review (SAR) | The purpose of this meeting is to review the key architectural decisions. Details of the design are not generally presented. This review will assess if the preliminary product design can meet the functional requirements with adequate margin for manufacturing.
Preliminary Design Review (PDR) | The PDR is a multi-disciplined technical review to ensure that the system under review can proceed to development of EDM systems, and can meet the stated performance requirements within cost (program budget), schedule (program schedule), risk, and other system constraints.
Critical Design Review (CDR) | The critical design review is held after EDM systems have been developed and DVT is complete. Like the PDR, the CDR is a multi-disciplined technical review to ensure that the system under review can proceed to production and can meet the stated performance requirements within cost, schedule, risk, and other system constraints Completion of CDR provides authorization to order production material for LRIPs and beyond.
Test Readiness Review (TRR) | A formal review of all documentation to ensure the design is ready to be Tested (Validated).
Product Readiness Review (PRR) | This is the final review in the NPI process. Completion of this milestone signifies the product is ready for full production.

## Slide 9: Appendix C: Personnel and Oversight
Title | Description
Project Team | A team that provides day-to-day management to the Project from initial phase through the Launch Phase.
Product Line Manager | The product manager assigned to the project. The person is primarily responsible for customer features, and product business aspects.
Engineering Project Manager | The Engineer assigned to the project that guides the project through the process up to Phase 4B. This manager is primarily responsible for leading the core team in the product development.
Manufacturing Engineer | Manufacturing individual responsible for transitioning the project to the manufacturing line, and for making sure all manufacturing related checklist items are completed at each phase. This would also include field service and in house service centers.

## Slide 10: Appendix D: Definitions
Term/Document | Notes/Comments
First Article Inspection | The first article inspection (FAI) is performed on LRIP or early production units to verify that the product is manufactured and tested in accordance with the product and part specifications. For the FAI, the unit which is evaluated must be built entirely by manufacturing.
Design History File | A folder in the engineering network directory which contains design documents, notes from reviews (CDR, PDR, SAR, etc) and relevant project planning documents (NPI checklists, etc).
Release | Placing a work product or deliverable under change control so subsequent changes are tracked and approved
Product Requirement Document | Describes the high-level performance requirements for the product.
Engineering Functional Requirements | Describes how engineers intend to solve the problems and design to the requirements (often listed in the Product requirements document). Provides guidance for engineers so they know what to design to.
Product Specification Document | Describes in detail each of the specifications for the product and serves as the basis for design verification. These specifications ensure that product requirements are met. This doc serves as the basis for verification.
Qualification Plan | Describes how spec verification and testing will be performed. Includes types of equipment.
Manufacturing Plan | This is the plan for how manufacturing will be performed. It includes determining resources requirements, floor space, beamlines, equipment etc. This may be done informally or through the use of the Manufacturing Plan Checklist
Verification | Confirmation, through the provision of objective evidence, that specified requirements have been fulfilled. ISO 9000:2015
Validation | Confirmation, through the provision of objective evidence, that the requirements for intended use or application have been fulfilled. ISO 900:2015
Qualification | This is generally meant to refer to the process a customer performs on the product to ensure it meets the requirements and expectations of a program.

## Slide 11: Appendix E: Product Development Material
Tool | Notes/Comments
Subassembly | Subassemblies are assembled units which form part of the overall system. In the NPI process, subassemblies may be selectively used for design verification, qualification or reliability testing. Subassemblies are typically tested in NPI phase 3 and 4.
EDM | Engineering Design model or systems. These are the initial engineering prototypes. Typically these systems are built in the engineering lab with engineering purchased material. These systems are used for verification testing. These systems are typically built in NPI phases 4 and 5. These systems are not sold to customers.
LRIP | These systems are initial production system, produced on the production floor with production material. Assembly of these systems is done in NPI phase 5 and 6 with the joint effort of Engineering and Manufacturing. These systems may be sold to customers, with customer notification that they are LRIPs. Once the following tasks have been completed, the systems are no longer deemed LRIP units and no special notification of the customer is required: build of systems identified in LRIP plan without significant failures, ATP release and successful passage, and release of all assemblies, subassemblies, and components at least to numeric level.
Production | Ongoing production systems which are built after NPI phase 5.

## Slide 12
Revision History |  |  | 
Rev | Release | Author | Description/Reason for Change
A |  |  | 
B |  |  | 
C |  |  | 
D |  |  | 
E |  |  |